## Bill of Materials
Sample Snatchers - Bill of Materials
Components that come in bulk quantity have had their price modified to the amount that will realistically be used. This amount will generally be estimated to be higher than lower. Each section has a name scheme to identify components later on quickly. Quantities will be updated more accurately as the final design is developed.
Battery and Power Delivery (PDXX)
Item # | Part | Vendor | Description | Qty | Cost | Link for Purchase
PD01 | 22 awg Wire | Amazon | Wires for connecting components to circuit | 1 | 0.8 | Generic
PD02 | XT60 Connectors | Aliexpress | Connectors for battery pack | 1 | 1.6 | Link
PD03 | 16 awg Wire | Amazon | Wires for 12v components | 1 | 0.8 | Generic
PD04 | P42A Molicel Battery 21700 | 18650 Battery | For battery pack assembly | 3 | 15 | Link
PD05 | 3S Battery Management System | Aliexpress | For safety | 1 | 2.94 | Link
PD07 | LM2596 | Aliexpress | Step down buck converter, 36V/24V/12V/5V/3V | 1 | 0.45 | Link
Control and Logic (CLXX)
Item # | Part | Vendor | Description | Qty | Cost | Link for Purchase
CL01 | ESP32-WROOM-C3 | Elegoo | Controller w/ Wifi + BT | 1 | 9.99 | Link
CL02 | H-Bridge Motor Driver BTS7960 | Aliexpress | Driving 12V motor for scraping | 1 | 7.41 | Link
CL03 | HX711 Sensor | Aliexpress | Strain gauge for mass analysis | 1 | 1.8 | Link
Measurement (MXX)
Item # | Part | Vendor | Description | Qty | Cost | Link for Purchase
M01 | 100g Load Cell | Aliexpress | Strain gauge to measure mass | 1 | 4.93 | Link
Structural Components (SCXX)
Item # | Part | Vendor | Description | Qty | Cost | Link for Purchase
SC01 | PLA - ~0.5 KG | Bambu | Filament for chassis | 1 | 7.99 | Link
SC02 | M3 Female Threaded Insert | Aliexpress | Heat set threaded inserts for chassis | 1 | 0.8 | Link
SC03 | M3/M4 Machine Screws | Aliexpress | Various length M3 Machine Screws | 1 | 1 | Generic
SC04 | 608 ZZ 608RS | Aliexpress | Ball bearings | 3 | 1.8 | Link
Sampling Tooling Components (STXX)
Item # | Part | Vendor | Description | Qty | Cost | Link for Purchase
ST01 | MGEHR1212 + Bits | Aliexpress | Lathe Bit and armature | 1 | 9.28 | Link
ST02 | GB37-520 7rpm 12v Motor | Aliexpress | For moving the armature with lathe bit | 1 | 11.28 | Link
Total | 77.87
Equipment
| Soldering Iron | Used to connect electrical components together
| Bambu Lab A1 3D Printer | Fused deposition modelling tool for additive manufacturing of chassis
| Heat Gun | Used for shrinking heat shrink
| Fume Extractor | Removes dangerous fumes created from soldering
| Screwdriver | Connecting and disconnecting basic hardware
| Breadboards | Useful for prototyping components, may be used in final design, cost will not be accounted
| Multimeter | Helpful for testing the circuits and their connections
| USB-C Chargers | Charges the devices used
| USB-C Cables | Transfers data and power from charges and laptops to devices, used to flash microcontroller
| Computer | For rendering and visualization
| Spot Welder | For rendering and visualization
Software
| Keyshot | For rendering and visualization
| Onshape | CAD Modeling software with collaborative tools and version control
| Arduino IDE | Programming environment with useful integrated libraries for compilation
| Google Sheets | For creating tables, BOMs, and logging data
| KiCAD | For creating custom circuitry and PCB designs
| Python | Used for making scripts to read and file incoming serial data

## Sheet12
Battery and Power Delivery (PDXX)
Item # | Part | Vendor | Description | Qty | Cost
PD01 | 22 awg Wire | Amazon | Wires for connecting components to circuit | 1 | 0.8
PD02 | XT60 Connectors | Aliexpress | Connectors for battery pack | 1 | 1.6
PD03 | 16 awg Wire | Amazon | Wires for 12v components | 1 | 0.8
PD04 | P42A Molicel Battery 21700 | 18650 Battery | For battery pack assembly | 3 | 15
PD05 | 3S Battery Management System | Aliexpress | For safety | 1 | 2.94
PD07 | LM2596 | Aliexpress | Step down buck converter, 36V/24V/12V/5V/3V | 1 | 0.45
Control and Logic (CLXX)
Item # | Part | Vendor | Description | Qty | Cost
CL01 | ESP32-WROOM-C3 | Elegoo | Controller w/ Wifi + BT | 1 | 9.99
CL02 | H-Bridge Motor Driver BTS7960 | Aliexpress | Driving 12V motor for scraping | 1 | 7.41
CL03 | HX711 Sensor | Aliexpress | Strain gauge for mass analysis | 1 | 1.8
Measurement (MXX)
Item # | Part | Vendor | Description | Qty | Cost
M01 | 100g Load Cell | Aliexpress | Strain gauge to measure mass | 1 | 4.93
Structural Components (SCXX)
Item # | Part | Vendor | Description | Qty | Cost
SC01 | PLA - ~0.70 KG | Bambu | Filament for chassis | 1 | 16.99
SC02 | M3 Female Threaded Insert | Aliexpress | Heat set threaded inserts for chassis | 1 | 0.8
SC03 | M3/M4 Machine Screws | Aliexpress | Various length M3 Machine Screws | 24 | 1
Sampling Tooling Components (STXX)
Item # | Part | Vendor | Description | Qty | Cost
ST01 | Lathe Bit | Aliexpress | Lathe Bit and armature | 1 | 3.25
ST02 | JGB37-520 7rpm 12v Motor | Aliexpress | For moving the armature with lathe bit | 1 | 11.28
Movement (MVXX)
Item # | Part | Vendor | Description | Qty | Cost
MV01 | Bearings | Aliexpress | For reducing friction and precise movement | 8 | 4.69
MV02 | N20 12V 200RPM | Aliexpress | Moves the device through the pipe | 2 | 10.78
MV03 | Rubber Bands | Amazon | Increases Friction of wheels, prevents slippage | 8 | 1.68
|  |  |  | Total: | 96.19

## Sheet11
Battery and Power Delivery (PDXX)
Item # | Part | Vendor | Description | Qty | Cost | Link for Purchase
PD01 | 22 awg Wire | Amazon | Wires for connecting components to circuit | 1 | 0.8 | Generic
PD02 | XT60 Connectors | Aliexpress | Connectors for battery pack | 1 | 1.6 | Link
PD03 | 16 awg Wire | Amazon | Wires for 12v components | 1 | 0.8 | Generic
PD04 | P42A Molicel Battery 21700 | 18650 Battery | For battery pack assembly | 3 | 15 | Link
PD05 | 3S Battery Management System | Aliexpress | For safety | 1 | 2.94 | Link
PD07 | LM2596 | Aliexpress | Step down buck converter, 36V/24V/12V/5V/3V | 1 | 0.45 | Link
Control and Logic (CLXX)
Item # | Part | Vendor | Description | Qty | Cost | Link for Purchase
CL01 | ESP32-WROOM-C3 | Elegoo | Controller w/ Wifi + BT | 1 | 9.99 | Link
CL02 | H-Bridge Motor Driver BTS7960 | Aliexpress | Driving 12V motor for scraping | 1 | 7.41 | Link
CL03 | HX711 Sensor | Aliexpress | Strain gauge for mass analysis | 1 | 1.8 | Link
Measurement (MXX)
Item # | Part | Vendor | Description | Qty | Cost | Link for Purchase
M01 | 100g Load Cell | Aliexpress | Strain gauge to measure mass | 1 | 4.93 | Link
Structural Components (SCXX)
Item # | Part | Vendor | Description | Qty | Cost | Link for Purchase
SC01 | PLA - ~0.5 KG | Bambu | Filament for chassis | 1 | 7.99 | Link
SC02 | M3 Female Threaded Insert | Aliexpress | Heat set threaded inserts for chassis | 1 | 0.8 | Link
SC03 | M3/M4 Machine Screws | Aliexpress | Various length M3 Machine Screws | 1 | 1 | Generic
SC04 | 608 ZZ 608RS | Aliexpress | Ball bearings | 3 | 1.8 | Link
Sampling Tooling Components (STXX)
Item # | Part | Vendor | Description | Qty | Cost | Link for Purchase
ST01 | MGEHR1212 + Bits | Aliexpress | Lathe Bit and armature | 1 | 9.28 | Link
ST02 | GB37-520 7rpm 12v Motor | Aliexpress | For moving the armature with lathe bit | 1 | 11.28 | Link
Total | 77.87

## Prototype Task Plan
Task | Owner Email | Status | Start date | End date | Task Duration (Days) | Description | Project Risks | Contingency Plan
CAD Model for Chassis | Tiam Morrow-Rogers | Completed | 2025-02-21 | 2025-02-23 | 2 | Develop the CAD Model for the chassis, integrating other components | Needs to contain all other components | Consistent redesign and maintenance
CAD Model for Scraper | Isaac Pinarski | Completed | 2025-02-21 | 2025-02-26 | 5 | Develop the CAD Model to be 3D printed that connect the scraping components | Doesn't collect a sample effectivley | Switch to drill ideation
Print Prototype 1 Components | Tiam Morrow-Rogers | Completed | 2025-02-21 | 2025-02-27 | 6 | Print all components for assembly of parts | Print failures | Resolve CAD models
CAD Model for Load Cell | Tiam Morrow-Rogers | Completed | 2025-02-21 | 2025-02-28 | 7 | Develop the CAD Model for the load cell sensor | Load cell is not accurate enough | Espresso scale and camera
CAD Model for Container | Eden Irwin | Completed | 2025-02-21 | 2025-03-05 | 12 | Develop the CAD model for the container | Container may affect accuracy of the load cell if in contact with other surfaces | New containment methods may have to be researched
CAD Model for Movement Device | radhe | Completed | 2025-02-21 | 2025-03-15 | 22 | Develop the CAD Model for wheels | Doesn't deploy effectively, not able to be sealed | Switch to motorized ideation
Prototype 1 Assembly | Group 16 | Completed | 2025-02-25 | 2025-02-28 | 3 | Assemble all components for the first prototype | Components do not fit together properly | Reprint components, test with lofi testing rig
CAD Model Bearing Mount | tiambennett@gmail.com | Completed | 2025-02-25 | 2025-03-05 | 8 | Allows the model to more freely move in the tube | Bearings might affect model size, they're needed to allow device to move freely | Adjusting chassis and mounting hardware for bearings
Electronics for Prototype 1 | Tiam Morrow-Rogers | Completed | 2025-02-26 | 2025-02-28 | 2 | Develop a functioning circuit for testing (Lo-Fi breadboard) | Components do not arrive in time | Purchase alternative components from local businesses
Test Prototype 1 | Group 16 | Completed | 2025-02-27 | 2025-02-28 | 1 | Test Sampling Prototype 1 (LoFi Focused) + record results (Prototyping Plan) | Isn't capable of sampling | Prototype 2
Print Prototype 2 Components | Tiam Morrow-Rogers | Completed | 2025-03-01 | 2025-03-05 | 4 | Print all components for assembly of parts | Print failures | Resolve CAD models
Test Prototype 2 | Group 16 | Completed | 2025-03-01 | 2025-03-07 | 6 | Test Obtainment of Prototype 2 (LoFi Focused) + record results (Prototyping Plan) | scraper rotates the device rather than scraping, the device torque is not sufficent enough to cut the material | drilling method (requires two motors) OR try stabilizing with rollers - considering friction (i.e. rubber coating)
Container with Load Cell Assembly | Group 16 | Completed | 2025-03-02 | 2025-03-05 | 3 | Assemble all components for the second prototype | Components do not fit together properly | Reprint components, test with lofi testing rig
Scraping CAD Model | Group 16 | Completed | 2025-03-02 | 2025-03-12 | 10 | Create the model for the scraping tool | Movement can't exceed the space of the device, has to effectively scrape | Test new bits, shorten armature, use higher torque motor
Scraping 3D Print | Tiam Morrow-Rogers | Completed | 2025-03-09 | 2025-03-14 | 5 | Print all components for assembly of parts | Print failures | Resolve CAD Models
Scraping Assembly | Group 16 | Completed | 2025-03-12 | 2025-03-15 | 3 | Assemble and Test scraping assembly | Ineffective scraping | Test new bits, shorten armature, use higher torque motor
Prototype 5 Assembly | Group 16 | Completed | 2025-03-14 | 2025-03-15 | 1 | Assemble all components for the fifth prototype (from previous prototyping) | Components do not fit together properly | Adjust CAD models, reprint components, test with lofi testing rig
Test Prototype 5 | Group 16 | Completed | 2025-03-15 | 2025-03-21 | 6 | Movement, Sampling & Power System Prototype | Device is incapeable of movment | Switch to higher torque motors, adjust the wheels to provide more friction
Print Prototype 5 Components | Tiam Morrow-Rogers | Completed | 2025-03-19 | 2025-03-22 | 3 | Print all components for assembly of parts | Print failures | Resolve CAD models
UX Wireframe/ User Interface | Eden Irwin | Completed | 2025-03-14 | 2025-03-21 | 7 | Develop a UX wireframe for the app - develop a more comprehensive prototype in Figma for user interactions | The app is NOT easy to follow and does not contain all of the desired information describing operating guidelines. | Re-design & survey
Presentation Board | Group 16 | Completed | 2025-03-21 | 2025-03-26 | 5 | Create a presentation board pertaining to the requirements specified in Deliverable I | The design of the board can include "too much" information & not be pleasing to the eye. | Re-design
Presentation Pitch | Group 16 | Completed | 2025-03-21 | 2025-03-26 | 5 | Create a 3 minute pitch presentation for the client/ judges meeting the specified requirements in Deliverable I | The pitch is too long, too short, does not contain all required information. | Re-organize content in a concise manner, practice, time, and practice again!
Whole System Prototype (Add containment) | Group 16 | Completed | 2025-03-21 | 2025-03-26 | 5 | Add the containment system prototype to Prototype 5 | The addition of the containment device is not feasible withthe current design. | Re-design/refine the containment component
Whole System Test | Group 16 | Completed | 2025-03-21 | 2025-03-26 | 5 | The team will continue to test the operation process of the device (following the prototyping test plan) | The device does not work. | Try to improve and refine design in a short time period, in time for Design Day.
Life-Cycle Analysis Pitch | Group 16 | Completed | 2025-03-21 | 2025-03-26 | 5 | The team will research, define, and create our pitch for the Life-Cycle analysis principles project. | Generally, devices used in nuclear reactors are designed explicitly with a cradle-to-grave mindset. A cradle-to-cradle pitch might be unrealistic. | Instead of focusing on how to make the device cradle-to-cradle, we can focus on its maintenance and how selected materials reduce waste and carbon footprint. Interior isolated components could also be cradle to cradle.

## Prototype Test Plan
Design Concept: |  | Inflatable Pipe Navigator
Test Number | Probable Critical Issue | Test Objective (Why) | Test Description (what) | Analysis Method (how and when) | Determine Measurables | Metrics | Level and Fidelity of Prototype (what) | Kind of Prototype (what) | Stopping Criterion | Results | Interpretation and Feedback | Notes
| What assumption are you testing? | Communication, Performance Measurement, Risk Management, Learning/Understanding | What specifically will you test? What is your hypothesis? | Specifically how will you test, include things like duration, sequence of test, equipment, pass/fail criteria etc. How will the results be collected? | What are you testing with your concept (target measurable attributes)? | What metrics will you test? What are the associated units? | HiFi/LoFi Focused, HiFi/LoFi Comprehensive | Visual, Analytical, Physical | The criterion for when the test is stopped | Observe and record results. | Pass or fail (include reason) and other feedback collected about prototype | 1. Include location of sketch, software libraries, reference materials, etc. 2. Take notes on how you can improve your next prototype 3. Other important things to remember
1 | Measurement of the collected sample | Performance Measurement (Load Cell Test) | Sample Weight Test: The sample is weighed accurately | The mass collected is of a specific quantity and is collected in the container. Measured by load cell sensor. 2 hours. | Sample collection weight | Mass: mg | HiFi - Focused | Physical | Can measure within a reasonable range | ±9.5mg | Pass, if sampling within 40-70mg the device will report back between 30-80mg which is acceptable. | Sketch located in Load Cell folder. Libraries used include Adafruit HX711 library. Utilized 100g load cell and HX 711. The next prototype will be implemented in the container.
2 | The sample is able to be collected | Performance Measurement (volume of collected sample) | Sample Obtainment Test: The device is able to remove material from the pipe | Visually inspect the material collected and weigh it. 2 hours estimated to complete. | Sample collection | Mass: mg | LoFi - Focused | Physical | A sample can be consistently collected | Motor Torque of 7rpm motor seems sufficient | Pass: The scraping bit was able to be scraped under very light pressure. Motor applies more than enough torque to the sample. Sample flakes are smaller than anticipated but still usable.
3 | The containter for the sample can open and close | Performance Measurement + Learning / Understanding | The sample container is able to close preventing operator contact. | Visually inspect and physically test the opening and closing mechanism of the sample container. | Size (fits all necessary components), usability (qualitative measurements) | Size (mm), mass (g), consistency (# of successful repetitions) | HiFi - Focused | Physical | Sample still consistenly measurable, user is able to consistently use the container | Lid opens and closes without the user requiring input. Mechanism automatically contains the sample. | Pass: The container effectively seals the sample, and also has the benefit of measuring the mass inside. Some modifications need to be made for the final model to work smoothly. | Sketch located in load cell folder. Same libraries as test 1. Total amount of container designs tested is 3. May require reprint for final design to accomodate space.
4 | The device is able to position to the sample site | Performance Measurement (movement mechanism) | Movement Test: The device can reach the sample site and return to the user. | Measure time of task (seconds) and distance covered (ft) | Distance, time | Time: seconds Distance: ft | LoFi - Focused | Physical | The device can move back and forth from sample site with succession | TBD | TBD | TBD
5 | Carrying System | Learning/Understanding | Device is easy to carry, and put into the pressure tube without excessive exposure to the operator | TBD | UX Metrics | Qualitative data Time: seconds | LoFi - Comprehensive | Physical | Easy to handle. | TBD | TBD | TBD
6 | Battery Pack System | Performance Measurement, Risk Management | The battery pack assembely is able to supply power to the appropriate components. | Battery tester | Power supplied | Voltage: volts Amps: coulombs Watts: joules per second | HiFi- Focused | Physical | Once the battery pack can supply 12 volts | The battery pack was able to supply 12 volts | Pass: the battery pack was able to supply 12 volts in order to power the motors | Sketch is located in battery pack components folder.
7 | User Interface | Communication, Learning/Understanding | The process operating the device is easy for the operator to use | Measure time of task (seconds). Results will be collected by surveying potential users on content and procedure. |  |  | HiFi- Focused | Visual | The application is easy to follow for the user, meeting all required components to operate the device and obtain feedback. | Based on survey, the application is easy to follow and obtains all the necessary parameters. | Pass, the application alone is simple and effective to demonstrate the procedure the operator would take to use the device. | The prototype will be shown on TabS9+ (on Design Day). For future improvements, the interface should be integrated into the actual design.
8 | Sampling, Movement, Power | Performance Measurement (All systems, minus containment) | Sampling, Containment, Power Test: The individual prototype systems piece together and function simultaneously. | Measure time of task (i.e. move to sample site, scrape sample, and reutn to operator). Results will be collected by timining the duration the operation takes. | Time of operation | Time: seconds | HiFi - Comprehensive | Physical | Motors run, device slides down pipe, device scrapes the pipe wall. | The motors were successfully powered, and the device moved efficiently. Scraping was unsuccesful. | The tool bit mount is not sufficient for the motor's torque. The materials we have access to will not overcome this barrier. | All other components work as expected. Motorized components haven't been added to the bearings, but we have been able to test the ability of the device to slide and are confident that it will move. Test 4 will be conducted on Monday and Tuesday. Carrying system will also be implemented later, the testing for this is not as crucial.

## Deliverable B - Needs Identific
Questions | User Statement | Interpreted Need | [10 empty] | Isaac
Typical Uses | To take a sample from the inside of a tube | The sample collected can be varied
| Limits exposure to operator | Sample is contained to limit exposure | [7 empty] | Number | Need | Importance (1-5, 5 highest)
Likes - Current Tool | All parts can be removed from the tube | Design can be completely removed | [7 empty] | 1 | The sample collected can be varied | 4
| Can be moved around by one individual | Should be modular/lightweight | [7 empty] | 2 | Sample is contained to limit exposure | 5
| The device is able to be powered with available resources | Necessary power sources should be included | [7 empty] | 3 | Design can be completely removed | 5
| Operator is informed of the status of the machine | The design is able to report current stage in it's process |  | Ang | Eden | Isaac | Tiam | Radhe |  | 4 | Should be modular/lightweight/ | 3
Dislikes - Current Tool | Client loves many things about existing device | Is a novel creative solution |  | 4 | 4 | 4 | 4 | 3 | 3.8 | 5 | Necessary power sources should be included | 4
|  |  |  | 5 | 5 | 5 | 5 | 5 | 5 | 6 | The design is able to report current stage in it's process | 4
Suggestions | Russian nesting doll the sample | Sample is contained by multiple layers |  | 4 | 5 | 5 | 5 | 5 | 4.8 | 7 | Is a novel creative solution | 2
| Your device must operate within the timeframe on design day | Device is reasonably fast |  | 4 | 3 | 3 | 4 | 4 | 3.6 | 8 | Sample is contained by multiple layers | 4
|  |  |  | 4 | 3 | 4 | 3 | 3 | 3.4 | 9 | Device is reasonably fast | 2
|  |  |  | 3 | 4 | 4 | 3 | 5 | 3.8
Number | Need | Importance (average team response) | 5 - critical | 3 | 3 | 2 | 3 | 5 | 3.2
1 | The sample collected can be varied | 3.8 | 4 - highly desirable | 3 | 3 | 4 | 3 | 4 | 3.4
2 | Sample is contained to limit exposure | 5 | 3 - nice | 2 | 2 | 2 | 2 | 2 | 2
3 | Design can be completely removed | 4.8 | 2 - not important
4 | Should be modular/lightweight | 3.6 | 1 - undesirable
5 | Necessary power sources should be included | 3.4
6 | The design is able to report current stage in it's process | 3.8
7 | Is a novel creative solution | 3.2
8 | Sample is contained by multiple layers | 3.4
9 | Device is reasonably fast | 2
Ideas
Device can be directly used in the hydrogen embrittlement test
Questions: | Do they test multiple tubes during one session?
General question about product benchmarking
Whatever your heart desires?
Tiam
Number | Need | Importance (1-5, 5 highest)
1 | The sample collected can be varied | 4
2 | Sample is contained to limit exposure | 5
3 | Design can be completely removed | 5
4 | Should be modular/lightweight/ | 4
5 | Necessary power sources should be included | 3
6 | The design is able to report current stage in it's process | 3
7 | Is a novel creative solution | 3
8 | Sample is contained by multiple layers | 3
9 | Device is reasonably fast | 2

## Maintence
qweqweqweqe
Part | Maintence Required | Frequencey
MOVMENT
Rubber Tread | Replacment | 1-2 years | Maintence: Replacement
Wheel Motors | Oil | 1-2 years
Wheel | Replacment | 3-4 years
Spool Rope | Replacment | 1-2 years
SAMPLING |  |  | Rubber Wheel Treads | Replacement | 3-5 years
Bit Head | Replacement | N/A | Bit Head | Replacement | N/A
Sampling Motor | Oil | 3-4 years
Bit Mount | Replacement | 0.5-1 year
POWER
Batteries | Replacment | 1-2 years
Wires | Replacment | 10-15 years
Battery Charge | Charge | 3-6 months
ESP32-WROOM-C3 | Replacment | 8-10 years
MEASURMENT
Load Cell | Replacment | 8-10 years
XT60 | Replacment | 6-7 yearrs

## Deliverable C - Design Criteria
Number | Need | High Priority | Design Criteria | ³
1 | Sample is contained to limit exposure | 🛟SAFETY🛟 | Thickness (mm) Material (Density)
2 | Design can be completely removed | 🛟SAFETY🛟 | Maneuverable
3 | The sample collected can be varied |  | 30mg - 80mg sample collection
4 | The design is able to report current stage in it's process |  | Display feedback
5 | Should be modular/lightweight |  | Weight (lbs) size (cm³)
6 | Necessary power sources should be included |  | Batteries/Compressed Air/Rat
7 | Is a novel creative solution |  | Unique (by comparison)
8 | Device is reasonably fast |  | Time (s)
🛟
Number | Need | High Priority | Design Criteria
1
2
3
4
5
6
7
8
1 | The sample collected can be varied |  | Importance (average team response)
2 | Sample is contained to limit exposure
3 | Design can be completely removed
4 | Should be modular/lightweight
5 | Necessary power sources should be included
6 | The design is able to report current stage in it's process
7 | Is a novel creative solution
8 | Sample is contained by multiple layers
9 | Device is reasonably fast

## Deliverable C - Product Benchma
Device Specifications ⬇️ | Device ➡️ | CWEST | Arterial Catheter | Drain Snake | CSA420 Endress
Company |  | Kinectrics |  |  | Endress & Hauser
Cost |  | $$$$$$$$$$ | $ | $ | $$$$
Stability
Shape |  | Tube | Wire | Wire | Tube |  |  |  | CSA420 Endress
Power |  | External: BRIMs |  | External: Man power | External: Man power |  |  |  | Sample Size | 10-50 mL
Failsafe |  | BRIMs | Pressure Drop | None | None |  |  |  | Tool Dimensions | length 381 mm x diameter 75 mm
Controls |  | BRIMs | None | Direct Hand |  |  |  |  | Weight | 1,55 kg to 6,1 kg
[9 empty] | Sample Containment | Device Housing- 316Ti stainless steel (Density= 7.9 g/cm³)
[5 empty] | a b |  |  |  | Speed | fast sampling interval
[6 empty] | Device Specifications ⬇️ | Device ➡️ | CWEST | Arterial Catheter | Drain Snake | CSA420 Endress | Mars Rover - Curiosity
[6 empty] | Company |  | Kinectrics | Generic | Generic | Endress & Hauser | NASA
[6 empty] | Cost |  | $$$$$$$$$$ | $ | $ | $$$ | $$$$$$$$$$$$$
[6 empty] | Stability |  | BRIMs | Guided by artery | None |  | Multiple surface contact points
[6 empty] | Shape |  | Tube | Wire | Wire | Tube | Rectangular
[6 empty] | Power |  | External: BRIMs | N/A | External: Man power | External: Man power | Solar + Radioisotope
[6 empty] | Failsafe |  | BRIMs | Pressure Drop | None | None | Safe-mode software, sensors
[6 empty] | Controls |  | BRIMs | Direct hand | Direct Hand | Control panel | Digital signalling
[6 empty] | Sampling Method |  | Scraping | Suction | Friction | Water Pressure | Drill, Scoop
[6 empty] | Size |  | ~4 ft | 20 gauge | 35.5” x 0.45” | 381 mm x 75 mm | 10’ x 9’7” x 7’
[6 empty] | Sample Size |  | 30-80mg | 1 mL | N/A | Liquid | 45mm³
[6 empty] | Material |  | Zirconium | Polyurethane, Silicone, Nitinol, Stainless Steel | plastic, metal | Polyamid PA, Stainless Steel | 7075 Aluminum, Titanium. Aerogel

## Deliverable C - EDS Requirement
Design Specifications |  | Relation (=, < or >) | Value | Units | Verification Method
Functional Requirements
1 | Collect a metal sample from tube wall | = | 30-80 | mg | Test
2 | Completely Removable | = | Yes | N/A | Test
3 | Enclosed Sample | = | Yes | N/A | Test
4 | Stage Reporting | = | Yes | N/A | Test
5 | Visual for process | = | Yes | in, dpi | Test
6 | Device speed | < | 7 | min | Test
7 | Power source included | = | Yes | N/A | Analysis
8 | Distance Traveled | = | 15 | ft | Test
Design Specifications |  | Relation (=, < or >) | Value | Units | Verification Method
Constraints
1 | Weight | < |  | kg | Analysis
2 | Size (Diameter) | < | 4 | in | Analysis
3 | Size (Length) | < | 4 | ft | Analysis
4 | Sample Exposure | < | Yes | N/A | Test
5 | Sample Collection | = | 30 - 80 | mg | Test
Design Specifications |  | Relation (=, < or >) | Value | Units | Verification Method
Non-Functional Requirements
1 | Aesthetics | = | Yes | N/A | Survey
2 | Safety | = | Yes | N/A | Analysis
3 | Corrosion Resistant | = | Yes | N/A | Analysis
4 | Operation Time | < | 10 | mins | Test
5 | Creative Solution | = | Yes | N/A | Analysis
https://www.amazon.com/product-reviews/B0C3L7FKCQ/ref=acr_dpx_hist_1?filterByStar=one_star&reviewerType=all_reviews
| Drain Snake |  |  |  |  | Arterial Catheter |  | https://ccforum.biomedcentral.com/articles/10.1186/cc1489#:~:text=In%20order%20to%20evaluate%20the,cannulation%20is%20a%20safe%20procedure.
[6 empty] | pros: | cons: | https://medneedles.ca/products/22g-x-1-bd-closed-iv-catheter-nexiva%E2%84%A2-sliding-safety-needle-box-of-20?_pos=8&_sid=a34526107&_ss=r&_gl=1*oi60p7*_up*MQ..*_gs*MQ..&gclid=CjwKCAiAqfe8BhBwEiwAsne6gbgi1azhBMQESqTDJvUX7QYbd2mTz81txL2Oyzzbddqs3CGcJXCoJBoCP1YQAvD_BwE
| Breaks Easily |  |  |  |  | simple to insert | expensive
| Doesnt collect materials properley (collection is not large enough) |  |  |  |  | easy to use | single use (material can degrade over time)
| Too short |  |  |  |  | provide real-time blood pressure readings, allowing for immediate adjustments in patient care | risk of infection
Cheap
Removes blockage
Reuseablility
Amazon.com. (2025, February 1). Customer reviews for 35.5inch Drain Clog Remover. Retrieved Febuary 1, 2025 from https://www.amazon.com/product-reviews/B0C3L7FKCQ/ref=cm_cr_arp_d_viewopt_kywd?filterByStar=five_star&reviewerType=all_reviews&pageNumber=1

## Deliverable E- Trello Board
Project Start Date: | 2025-01-19
Group Name | Sample Snatchers
|  |  |  | 2025-01-19 | [6 empty] | 2025-01-26 | [6 empty] | 2025-02-02 | [6 empty] | 2025-02-09 | [6 empty] | 2025-02-16 | [6 empty] | 2025-02-23 | [6 empty] | 2025-03-02
 | time axis 2025-01-19 to 2025-03-08
To Do | START DATE | DAYS | END | time axis 2025-01-19 to 2025-03-08
Task 2: Deliverable F - Prototype I and Customer Feedback | 2025-02-23 | 7 | 2025-03-02
Develop the first prototype (and get customer feedback) | 2025-02-23 | 7 | 2025-02-23 | bar: 2025-02-24 to 2025-03-02
Device a detailed test plan for the second prototype | 2025-02-23 | 7 | 2025-02-23 | bar: 2025-02-24 to 2025-03-02
Task 2: Deliverable G - Prototype II and Customer Feedback | 2025-03-02 | 7 | 2025-03-09
Detail feedback from the first prototype (and impacts for the next) | 2025-03-02 | 7 | 2025-03-09
Develop the second prototype (based on plan; "why", "what", "how") | 2025-03-02 | 7 | 2025-03-09
Document the prototyping test plan, analysis, and results of prototype | 2025-03-02 | 7 | 2025-03-09
Gather feedback from potential clients/users | 2025-03-02 | 7 | 2025-03-09
Update target specifications, detailed design, and BOM | 2025-03-02 | 7 | 2025-03-09
Device a detailed prototyping test plan (third prototype) | 2025-03-02 | 7 | 2025-03-09
In Progress | START DATE | DAYS | END
TASK 1: Deliverable E - Project Schedule and Cost | 2025-02-09 | 7 | 2025-02-16
A detailed design drawing summarizing chosen concept | 2025-02-09 | 7 | 2025-02-16
A list of all design part (for chosen concept) | 2025-02-09 | 7 | 2025-02-16
An outlined plan for prototyping/testing including all required tasks, estimated duration, significant project risks | 2025-02-09 | 7 | 2025-02-16
A product/project cost spreadsheet (Bill of Materials - BOM) | 2025-02-09 | 7 | 2025-02-16
A list of equipment (software or hardware) | 2025-02-09 | 7 | 2025-02-16
An outlined prototyping test plan | 2025-02-09 | 7 | 2025-02-16
Define a stopping criterion | 2025-02-09 | 7 | 2025-02-16
Completed | START DATE | DAYS | END
TASK 1: Deliverable B - Needs Identification and Problem Statement | 2025-01-19 | 7 | 2025-01-26
Client Interaction and Need Identification | 2025-01-19 | 7 | 2025-01-26
Interpreted Needs Statements | 2025-01-19 | 7 | 2025-01-26
Formulate Problem Statement | 2025-01-19 | 7 | 2025-01-26
User Benchmarking | 2025-01-19 | 7 | 2025-01-26
Document Structure and Compilation | 2025-01-19 | 7 | 2025-01-26
Team Review and Quality Assurance | 2025-01-19 | 7 | 2025-01-26
TASK 2: Assignment 2 - Peer Feedback Evaluation and Team Dynamics (2.1) | START DATE | DAYS | END
Peer Feedback Deliverable- Tiam Morrow-Rogers | 2025-02-02 | 7 | 2025-02-09
Peer Feedback Deliverable- Ang Li | 2025-02-02 | 7 | 2025-02-09
Peer Feedback Deliverable- Eden Irwin | 2025-02-02 | 7 | 2025-02-09
Peer Feedback Deliverable- Radhe Pandey | 2025-02-02 | 7 | 2025-02-09
Peer Feedback Deliverable- Isaac Pinarski | 2025-02-02 | 7 | 2025-02-09
TASK 3: Deliverable D | 2025-02-02 | 7 | 2025-02-09
Identify and Design Subsytems (Movement, sampling, power, feedback, etc.) | 2025-02-02 | 7 | 2025-02-09
Concept Development of Subsystems | 2025-02-02 | 7 | 2025-02-09
Group Ideations | 2025-02-02 | 7 | 2025-02-09
Team Discussion and Feedback | 2025-02-02 | 7 | 2025-02-09
Combine Subsystem Concepts (3 Solutions) | 2025-02-02 | 7 | 2025-02-09
Document Illustrations | 2025-02-02 | 7 | 2025-02-09
Validate Problem Statement | 2025-02-02 | 7 | 2025-02-09
Prepare Concept Slides | 2025-02-02 | 7 | 2025-02-09

## Deliverable G- Trello Board
Project Date: | 2025-02-02
Group Name | Sample Snatchers
|  |  |  | 2025-02-02 | [6 empty] | 2025-02-09 | [6 empty] | 2025-02-16 | [6 empty] | 2025-02-23 | [6 empty] | 2025-03-02 | [6 empty] | 2025-03-09 | [6 empty] | 2025-03-16
 | time axis 2025-02-02 to 2025-03-22
To Do | START DATE | DAYS | END | time axis 2025-02-02 to 2025-03-22
TASK 1: Deliverable I - Design Day | 2025-03-19 | 7 | 2025-03-26
TASK 2: Deliverable H - Prototype III and Customer Feedback | 2025-03-16 | 7 | 2025-03-23
Prototyping (The "Why") | 2025-03-16 | 7 | 2025-03-23
Analysis and Feedback | 2025-03-16 | 7 | 2025-03-23
Test Plan (Prototype 2) | 2025-03-16 | 7 | 2025-03-23
Project Task, Plan Maintenance and Task Assignment | 2025-03-16 | 7 | 2025-03-23
In Progress | START DATE | DAYS | END
TASK 1: Deliverable G - Prototype II and Customer Feedback | 2025-03-02 | 7 | 2025-03-09
Develop the first prototype (and get customer feedback) | 2025-03-02 | 7 | 2025-03-09
Device a detailed test plan for the second prototype | 2025-03-02 | 7 | 2025-03-09
TASK 2: Deliverable J - Final Project Presentations | 2025-03-05 | 7 | 2025-03-12
Solution options and chosen concept (why/how) | 2025-03-05 | 7 | 2025-03-12
Decisions made | 2025-03-05 | 7 | 2025-03-12
Trials and tribulations, lessons learned, future work, etc. | 2025-03-05 | 7 | 2025-03-12
Completed | START DATE | DAYS | END
TASK 1: Assignment 2 - Peer Feedback Evaluation and Team Dynamics (2.1) | START DATE | DAYS | END
Peer Feedback Deliverable- Tiam Morrow-Rogers | 2025-02-02 | 7 | 2025-02-09
Peer Feedback Deliverable- Ang Li | 2025-02-02 | 7 | 2025-02-09
Peer Feedback Deliverable- Eden Irwin | 2025-02-02 | 7 | 2025-02-09
Peer Feedback Deliverable- Radhe Pandey | 2025-02-02 | 7 | 2025-02-09
Peer Feedback Deliverable- Isaac Pinarski | 2025-02-02 | 7 | 2025-02-09
TASK 2: Deliverable E - Project Schedule and Cost | 2025-02-16 | 7 | 2025-02-23
A detailed design drawing summarizing chosen concept | 2025-02-16 | 7 | 2025-02-23
A list of all design part (for chosen concept) | 2025-02-16 | 7 | 2025-02-23
Formulate Problem Statement | 2025-02-16 | 7 | 2025-02-23
User Benchmarking | 2025-02-16 | 7 | 2025-02-23
Document Structure and Compilation | 2025-02-16 | 7 | 2025-02-23
Team Review and Quality Assurance | 2025-02-16 | 7 | 2025-02-23
TASK 3: Deliverable F - Prototype I and Customer Feedback | 2025-02-23 | 7 | 2025-03-02
Develop the first prototype (and get customer feedback) | 2025-02-23 | 7 | 2025-03-02
Document analysis and results from tests (using Prototyping Test Plan) | 2025-02-23 | 7 | 2025-03-02
Update target specifications, detailed design, and Bill of Materials (BOM) | 2025-02-23 | 7 | 2025-03-02
Device a detailed test plan for the second prototype | 2025-02-23 | 7 | 2025-03-02

## Deliverable H- Trello Board
Project Date: | 2025-02-23
Group Name | Sample Snatchers
|  |  |  | 2025-02-23 | [6 empty] | 2025-03-02 | [6 empty] | 2025-03-09 | [6 empty] | 2025-03-16 | [6 empty] | 2025-03-23 | [6 empty] | 2025-03-30 | [6 empty] | 2025-04-06
 | time axis 2025-02-23 to 2025-04-12
To Do | START DATE | DAYS | END | time axis 2025-02-23 to 2025-04-12
TASK 1: Deliverable I - Design Day | 2025-03-19 | 7 | 2025-03-26
TASK 2: Deliverable K - User Manual | 2025-03-28 | 7 | 2025-04-04
In Progress | START DATE | DAYS | END
TASK 1: Deliverable H - Prototype III and Customer Feedback | 2025-03-16 | 7 | 2025-03-23
Prototyping (The "Why") | 2025-03-16 | 7 | 2025-03-23
Analysis and Feedback | 2025-03-16 | 7 | 2025-03-23
Test Plan (Prototype 2) | 2025-03-16 | 7 | 2025-03-23
Project Task, Plan Maintenance and Task Assignment | 2025-03-16 | 7 | 2025-03-23
Completed | START DATE | DAYS | END
TASK 1: Deliverable F - Prototype I and Customer Feedback | 2025-02-23 | 7 | 2025-03-02
Develop the first prototype (and get customer feedback) | 2025-02-23 | 7 | 2025-03-02
Document analysis and results from tests (using Prototyping Test Plan) | 2025-02-23 | 7 | 2025-03-02
Update target specifications, detailed design, and Bill of Materials (BOM) | 2025-02-23 | 7 | 2025-03-02
Device a detailed test plan for the second prototype | 2025-02-23 | 7 | 2025-03-02
TASK 2: Deliverable G - Prototype II and Customer Feedback | 2025-03-02 | 7 | 2025-03-09
Develop the first prototype (and get customer feedback) | 2025-03-02 | 7 | 2025-03-09
Device a detailed test plan for the second prototype | 2025-03-02 | 7 | 2025-03-09
TASK 3: Deliverable J - Final Project Presentations | 2025-03-05 | 7 | 2025-03-12
Solution options and chosen concept (why/how) | 2025-03-05 | 7 | 2025-03-12
Decisions made | 2025-03-05 | 7 | 2025-03-12
Trials and tribulations, lessons learned, future work, etc. | 2025-03-05 | 7 | 2025-03-12

## Copy of Deliverable F- Trello B
Project Date: | 2025-02-02
Group Name | Sample Snatchers
|  |  |  | 2025-02-02 | [6 empty] | 2025-02-09 | [6 empty] | 2025-02-16 | [6 empty] | 2025-02-23 | [6 empty] | 2025-03-02 | [6 empty] | 2025-03-09 | [6 empty] | 2025-03-16
 | time axis 2025-02-02 to 2025-03-22
To Do | START DATE | DAYS | END | time axis 2025-02-02 to 2025-03-22
TASK 1: Deliverable I - Design Day | 2025-03-19 | 7 | 2025-03-26
TASK 2: Deliverable H - Prototype III and Customer Feedback | 2025-03-16 | 7 | 2025-03-23
Prototyping (The "Why") | 2025-03-16 | 7 | 2025-03-23
Analysis and Feedback | 2025-03-16 | 7 | 2025-03-23
Test Plan (Prototype 2) | 2025-03-16 | 7 | 2025-03-23
Project Task, Plan Maintenance and Task Assignment | 2025-03-16 | 7 | 2025-03-23
In Progress | START DATE | DAYS | END
TASK 1: Deliverable G - Prototype II and Customer Feedback | 2025-03-02 | 7 | 2025-03-09
Develop the first prototype (and get customer feedback) | 2025-03-02 | 7 | 2025-03-09
Device a detailed test plan for the second prototype | 2025-03-02 | 7 | 2025-03-09
TASK 2: Deliverable J - Final Project Presentations | 2025-03-05 | 7 | 2025-03-12
Solution options and chosen concept (why/how) | 2025-03-05 | 7 | 2025-03-12
Decisions made | 2025-03-05 | 7 | 2025-03-12
Trials and tribulations, lessons learned, future work, etc. | 2025-03-05 | 7 | 2025-03-12
Completed | START DATE | DAYS | END
TASK 1: Assignment 2 - Peer Feedback Evaluation and Team Dynamics (2.1) | START DATE | DAYS | END
Peer Feedback Deliverable- Tiam Morrow-Rogers | 2025-02-02 | 7 | 2025-02-09
Peer Feedback Deliverable- Ang Li | 2025-02-02 | 7 | 2025-02-09
Peer Feedback Deliverable- Eden Irwin | 2025-02-02 | 7 | 2025-02-09
Peer Feedback Deliverable- Radhe Pandey | 2025-02-02 | 7 | 2025-02-09
Peer Feedback Deliverable- Isaac Pinarski | 2025-02-02 | 7 | 2025-02-09
TASK 2: Deliverable E - Project Schedule and Cost | 2025-02-16 | 7 | 2025-02-23
A detailed design drawing summarizing chosen concept | 2025-02-16 | 7 | 2025-02-23
A list of all design part (for chosen concept) | 2025-02-16 | 7 | 2025-02-23
Formulate Problem Statement | 2025-02-16 | 7 | 2025-02-23
User Benchmarking | 2025-02-16 | 7 | 2025-02-23
Document Structure and Compilation | 2025-02-16 | 7 | 2025-02-23
Team Review and Quality Assurance | 2025-02-16 | 7 | 2025-02-23
TASK 3: Deliverable F - Prototype I and Customer Feedback | 2025-02-23 | 7 | 2025-03-02
Develop the first prototype (and get customer feedback) | 2025-02-23 | 7 | 2025-03-02
Document analysis and results from tests (using Prototyping Test Plan) | 2025-02-23 | 7 | 2025-03-02
Update target specifications, detailed design, and Bill of Materials (BOM) | 2025-02-23 | 7 | 2025-03-02
Device a detailed test plan for the second prototype | 2025-02-23 | 7 | 2025-03-02

## Deliverable Ds- Trello Board
Project Start Date: | 2025-01-19
Group Name | Sample Snatchers
|  |  |  | 2025-01-19 | [6 empty] | 2025-01-26 | [6 empty] | 2025-02-02 | [6 empty] | 2025-02-09 | [6 empty] | 2025-02-16 | [6 empty] | 2025-02-23 | [6 empty] | 2025-03-02
 | time axis 2025-01-19 to 2025-03-08
To Do | START DATE | DAYS | END | time axis 2025-01-19 to 2025-03-08
TASK 1: Deliverable E - Project Schedule and Cost | 2025-02-09 | 7 | 2025-02-16
A detailed design drawing summarizing chosen concept | 2025-02-09 | 7 | 2025-02-16 | bar: 2025-02-09 to 2025-02-16
A list of all design part (for chosen concept) | 2025-02-09 | 7 | 2025-02-16 | bar: 2025-02-09 to 2025-02-16
An outlined plan for prototyping/testing including all required tasks, estimated duration, significant project risks | 2025-02-09 | 7 | 2025-02-16 | bar: 2025-02-09 to 2025-02-16
A product/project cost spreadsheet (Bill of Materials - BOM) | 2025-02-09 | 7 | 2025-02-16 | bar: 2025-02-09 to 2025-02-16
A list of equipment (software or hardware) | 2025-02-09 | 7 | 2025-02-16 | bar: 2025-02-09 to 2025-02-16
An outlined prototyping test plan | 2025-02-09 | 7 | 2025-02-16 | bar: 2025-02-09 to 2025-02-16
Define a stopping criterion | 2025-02-09 | 7 | 2025-02-16 | bar: 2025-02-09 to 2025-02-16
Task 2: Deliverable F - Prototype I and Customer Feedback | 2025-02-23 | 7 | 2025-03-02
Develop the first prototype (and get customer feedback) | 2025-02-23 | 7 | 2025-02-23 | bar: 2025-02-23 to 2025-02-28
Device a detailed test plan for the second prototype | 2025-02-23 | 7 | 2025-02-23 | bar: 2025-02-23 to 2025-02-28
In Progress | START DATE | DAYS | END
TASK 1: Deliverable D | 2025-02-02 | 7 | 2025-02-09
Identify and Design Subsytems (Movement, sampling, power, feedback, etc.) | 2025-02-02 | 7 | 2025-02-09
Concept Development of Subsystems | 2025-02-02 | 7 | 2025-02-09
Group Ideations | 2025-02-02 | 7 | 2025-02-09
Team Discussion and Feedback | 2025-02-02 | 7 | 2025-02-09
Combine Subsystem Concepts (3 Solutions) | 2025-02-02 | 7 | 2025-02-09
Document Illustrations | 2025-02-02 | 7 | 2025-02-09
Validate Problem Statement | 2025-02-02 | 7 | 2025-02-09
Prepare Concept Slides | 2025-02-02 | 7 | 2025-02-09
Completed | START DATE | DAYS | END
TASK 1: Deliverable A - Team Contract and Project Management Template | 2025-01-12 | 7 | 2025-01-19
TASK 2: Deliverable B - Needs Identification and Problem Statement | 2025-01-19 | 7 | 2025-01-26
Client Interaction and Need Identification | 2025-01-19 | 7 | 2025-01-26
Interpreted Needs Statements | 2025-01-19 | 7 | 2025-01-26
Formulate Problem Statement | 2025-01-19 | 7 | 2025-01-26
User Benchmarking | 2025-01-19 | 7 | 2025-01-26
Document Structure and Compilation | 2025-01-19 | 7 | 2025-01-26
Team Review and Quality Assurance | 2025-01-19 | 7 | 2025-01-26
TASK 3: Assignment 2 - Peer Feedback Evaluation and Team Dynamics (2.1) | START DATE | DAYS | END
Peer Feedback Deliverable- Tiam Morrow-Rogers | 2025-02-02 | 7 | 2025-02-09
Peer Feedback Deliverable- Ang Li | 2025-02-02 | 7 | 2025-02-09
Peer Feedback Deliverable- Eden Irwin | 2025-02-02 | 7 | 2025-02-09
Peer Feedback Deliverable- Radhe Pandey | 2025-02-02 | 7 | 2025-02-09
Peer Feedback Deliverable- Isaac Pinarski | 2025-02-02 | 7 | 2025-02-09